The Department of Veterans Affairs and Community Partners

Veteran’s Experience Action Center (VEAC)

Operation Plan and Procedures

2018-03VEAC/ Montgomery, AL/ December 5, 2018

Section									   Page

Mission Statement										3

Location Overview										3

Facility and hours of operation								3

Community Service Providers								4

Advertising and Public Contact								4

Security											4

Parking											5

Transportation										5

Veteran Engagement and Special Services						5

Signage and Décor										5

Site Plan											6

Staffing											7

Food and Beverage									8

Audio- Visual										8

Connectivity- Automation								8

Emergency Risk Management								8

Overall Power Requirement								8

Equipment List- Rentals and Purchases						9

Communication- Points of Contact							9

Contingency Plan										9

Documents and Diagrams						     Appendix A

Mission

The Department of Veterans Affairs, including the Veterans Benefits Administration, Veterans Healthcare Administration, National Cemetery Administrations, and The Vet Center will partner with The Alabama Division of Veterans Affairs, The Alabama Association of County Veterans Service Officers, ALAVETNET (Community Veterans Engagement Board), and multiple Community partners to provide services to Veterans, family members, caregivers and survivors in the regional area.  The Veterans support partnership will provide claims/appeals assistance, healthcare consultation and appointment scheduling, mental health counseling, and various community information and services offerings.

The intent of this event is to create collaborative partnership between Veterans service and support organizations of all types, on all levels of the government and the private sector respectively to address and attempt to solve issues experienced by each individual Veteran, family member, caregiver and survivor on the spot, at the VEAC.

Location Overview

The VEAC will be held at The Crampton Bowl Multiplex 220 Hall Street Montgomery, AL 36104

This location has suitable space, electrical power, and overall facility capabilities commensurate with the needs of the Veterans service task force.  Dorian Jenkins of the Alabama VA Regional Office and representatives from support organizations have conducted the pre- site survey on xx/xx/xx and have confirmed that all logistical and operational needs can be met at this location and by this facility staff.

Facility and Hours of Operation

The Hours of operation for VEAC 2018-03 will be as follows:

Wednesday 12/5/18- 9AM-3PM

Considerations

- Useable square footage

57,600 SQ FT

- Maximum capacity

BLDG#1- RFI

- Ceiling Height

30 FT

- Entrance/ Exit

Handicapped accessible entrances

- Disability Access- Yes

- Setup and breakdown hours

Setup 8AM- 12/5/18

Breakdown 3PM- 12/5/18

- In house support

Parking, Escort, Facility operations, Reception, Concessions, Maintenance

- Contract development (facilities)

TBD-

- Restroom facilities

Male and Female restrooms

- Wireless internet availability

Wi-Fi is sufficient to meet requirements of the task force

Community Providers

It is understood that there are many public, government and private organizations which are of great assistance to Veterans, families, caregiver and survivors.  These organizations are indispensable in providing service and support to those in attendance at the VEAC.  Placement and setup of the individual organizational display areas will be at the direction of the facility supervisor and/or lead organizer.  All vendors and service providers will be jointly vetted by the VA and the ALAVETNET (local CVEB).  Example community provider layouts are included in Appendix A- Documents and Diagrams at the end of this electronic document.

Advertising and Public Contact

The VA will utilize the following to widely broadcast the message regarding time and location of the VEAC in respective areas of Alabama.  The VA and ALAVETNET will collectively complete and disseminate an event flyer to all stakeholders no later than 30 days prior to the VEAC for review and subsequent release.

•Television

•Radio

•Print Publications

•Internet

•Direct Mail

•Signage

•Product Placement

•Mobile Devices

•Sponsorships

•Other Media Outlets

- ALAVETNET will compose and send invitations to all United States Senators from AL, the Congressman representing the respective District and the Mayor of Montgomery.

Security

The host organization and facility will be responsible to provide security commensurate with the projected public utilization rate and maximum capacity of the buildings.  It is incumbent upon the host facility to ensure that the facilities are locked and secure so that any professional equipment and documentation will be safeguarded during times which the VEAC is not staffed and operating.

Parking

The support staff will be authorized to park close to the building to download equipment and personnel.  VIP parking will be identified for distinguished guests who plan to attend. The local community is asked to provide volunteers (if needed) to direct incoming and outgoing vehicles into proper parking areas and respective spaces.

Transportation

Individual service organizations and other organizations involved in supporting the VEAC are asked to provide transportation for their respective support personnel and equipment to and from the event. The ALAVETNET is asked to explore transportation for prospective attendees who are not ambulatory or require transportation assistance to attend.

Attendee Engagement and Services

To take advantage of the gathering of Veterans, families, caregivers and survivors it is recommended that other events and information sessions be conducted to engage attendees while they wait on primary VEAC services. Some of these engagement activities may include, but not be limited to, VA benefits and healthcare information sessions; military equipment static displays by local military units; VEO VetTalkX; car and motorcycle shows; Veterans town hall (community sensing session); and community Veteran service and support fair.

The ALAVETNET, primary event partners, and/or NG/RES/Active Duty forces are asked to engage community partners to provide escorts and other volunteers to assist those attendees with special needs.

Signage and Décor

The ALAVETNET is asked to engage community partners to provide directional signage denoting the event location. Local government transportation agencies possess LED and other types of directional signs that may be utilized for directing motorized traffic to the event.

It is requested that The American Flag, Alabama state flag, Department of Veterans Affairs flag and flags denoting each of the major armed services be displayed in positions of prominence and in proper order.

Site Plan (EXAMPLE) – Photos and Diagram of host location

Staffing

The Montgomery ALAVETNET requests support from Veterans service partners in the form of staffing for the VEAC in the following quantities. Individual support organizations should provide feedback concerning the feasibility of providing the requested personnel NLT 12/5/18.

Veteran’s Benefits Administration- Minimum 10 personnel

- VBA contingent makeup dependent upon supervisor in charge decision

  - Recommended 70% RVSR, 20 % VSR, 10% AVSCM/VSCM/SES

- 1 X Ebenefits enrollment

Veteran’s Healthcare Administration- Minimum 4 personnel

- 1 X Eligibility and Enrollment in VHA healthcare (automated)

- 1 X My Healthe Vet enrollment person

- 1 X Patient Advocate/ Policy expert

- 1 X Appointment/ VA Exam scheduler

- Less than 4 VHA support personnel may be needed if dual role is performed.

The State Division of Veterans Affairs- Minimum 4 personnel (VSO/VST) per day

County Veterans Service Officers (host/surrounding county) - Minimum 4 personnel per day

-The VSO will act as the primary counsel and triage for the clients attending the VEAC.  The VSO will utilize technical knowledge and operational capability to correctly route the client to appropriate assistance entity and/or will counsel, file claims/appeals and advise the client on proper course of action.

-VSO should have an internet capable laptop and a personal printer (if possible) to fill and print electronic forms.

The American Red Cross- Minimum 2 personnel (Certified BLS and CPR qualified)

Vet Center- Minimum of 2 personnel (1 x clinician) and RV treatment vehicle

It is requested that all Veterans service partners and support personnel report no later than thirty minutes before start time.

Food and Beverage

Food and beverage may be provided for the Veterans service partners through donations by the local community, facilitated by the Montgomery ALAVETNET.  It is requested that the ALAVETNET make arrangement for meals to be delivered to the host facility.

It is recommended that the host facility provide basic concessions for attendees. Some clients may experience extended wait times during the VEAC.  Basic food and drink items at a reasonable price can serve to improve the overall experience at this event.

Audio-Visual

The host facility is asked to provide a public-address system capable of providing clear communication to VEAC clients in a noise filled environment.  The host facility is asked to provide visual entertainment for clients who are waiting to watch news or other widely acceptable, no partisan programs.

Connectivity and Automation

The host facility can provide a wireless internet network which will support up to thirty (30) computers and three (3) wireless network printers. Bandwidth requirements have been verified.  The individual agencies and support organizations will be responsible to provide automation for their contingent of personnel. It is requested that the host facility provide one (1) copier with paper for general use by the Veterans service task force. Individual service organizations are highly encouraged to have WiFi hotspots for use in case the organic services fail or are not capable of accommodating the needed bandwidth.

Emergency Risk Management

The facility or the VA will provide appropriate security forces to deal with situations that may pose a threat to the attendees or the facility. VA and host facility leaders will define appropriate number and function of the security forces and the responsible payment organization.

The facility supervisor is asked to confirm that fire extinguishers in the proper quantity are on hand and serviceable. It is requested that The American Red Cross provide a minimum of two personnel who are first aid and Basic Lifesaver qualified.  It is requested that the facility supervisor ensure the following are on hand within the facility.

- Fire evacuation plan with diagram

- Natural disaster evacuation plan

- Serious incident SOP (physical and weapons violence)

- Any other emergencies identified as possible

* It should be noted that there will be a large concentration of persons, equipment, automobiles and other apparatus in a very small area.  There is always a higher risk of injury and terrorist targeting with a concentration of population.

Overall Power Requirements

The host facility has been verified to have power provision capabilities to support the VEAC and all related operations.

Equipment List and Rentals

Tables and chairs

Provided by host facility

Pipe and Curtain (not required but HIGHLY recommended)

It is requested that the ALAVETNET engage the community to procure twelve (12) individual 8’ X 8’ pipe and curtain subsections. These sections will consist of six or eight (6 or 8) ft. high walls on two sides, a wall on one side and an open entrance side.

Communication

A list of contacts for each Veterans service task force partner and support organization will be released a minimum of 10 days prior to the VEAC.  This point of contact list will include name, email, office phone and mobile phone.  This information is of a sensitive nature and should be used only to conduct VEAC business.  This information is not authorized to be released to any party other than the individual it is provided to in association with the VEAC conduction.

Contingency Plan

The VEAC will be conducted as an indoor only event therefore the contingency plan, based on weather, is not a consideration.  In the event of natural disaster which affects the host location the ALAVETNET will advise all members of the Veterans service task force of changes in operational timeline and location.  The host facility is asked to have the following in preparation for unseen events which could curtail the success of the VEAC at their location.

- Phone, fax and email of all subcontractors supporting the post and/or VEAC

- Standby points of contact at the local electric and gas provider

- A media spokesperson to address such issues should they arise

Cajun A. Comeau

The Department of Veterans Affairs

Veterans Experience Office

Veteran, Family and Community Engagement

Senior Field Consultant, Southeast US

Cajun.comeau@va.gov

Mobile 980-579-9581

Appendix A- Documents and Diagrams

- Standard VEO VEAC Flyer

- Sample VEAC Layout- Charlotte NC 2017- Friendship Baptist Church

- Sample VEAC Program Guide- Charlotte VCAC 2017

- Standard VEO VEAC Social Media Marketing Templates. VEO VEAC Facebook event links https://www.facebook.com/events/403810777035489/ https://www.facebook.com/events/964240297247154/